## Summary View
Risk Description: | Likelihood | Impact | Priority | Preventative Action | Contingency Plans
Major natural catastrophe in NZ / Australia | L | H | H | The application is deployed on AWS infrastructure and dispersed across multiple Availability Zones (AZ) in the Asia Pacific Sydney Region. An AZ consists of one or more data centres at a location within an AWS Region. Each AZ has independent cooling, power, and physical security. | The application
|  |  |  | The database is an MySQL cluster with Multi AZ (multiple availability zones) enabled. | If an active AZ in a region is impacted, service provision will automatically transition to the next available AZ.
The database
In the event of a planned or unplanned outage of the Writer instance, Amazon RDS automatically switches to a standby replica in another AZ. The time it takes for the failover to complete depends on the database activity and other conditions at the time the primary DB instance became unavailable. Failover times are typically 60-120 seconds.
External attack on website (D-DOS) | M | H | H | AWS GuardDuty is configured for Clients. GuardDuty identifies threats by continuously monitoring the network activity, data access patterns, and account behaviour within the AWS environment | SM8 usually only has one end-point. Prevention techniques include;
· Blacklist suspicious IP addresses
· auto scale EC2 instances to ensure application remains operational.
Website overload – No Website Service | M | L | M | SM8 is deployed across multiple EC2 instances and sits behind a load balancer. The instance cluster is auto scaling. | With auto scaling, EC2 instances are automatically added or removed in response to demand load.
Website hacked or penetrated | M | H | H | Website security measures and pen-testing designed to prevent attacks. Databases in a private subnet. Applications in a IP whitelisted security group controlled public subnet. Application architecture employs SSL termination pattern. | Server restoration from latest backup after analysis and removal of vulnerability
Hosting provider experiences problems | L | L | L | Reputable/world leading hosting provider used (AWS) | AWS SLA has a 99.99% monthly uptime percentage. In the event of a full regional outage, the application would currently have to wait for the regional data centres to be restored.
Hardware failure | L | H | H | Reputable hosting equipment and technologies used, reliance on world-leading cloud-hosting service (AWS) | AWS SLA has a 99.99% monthly uptime percentage. In the event of a full regional outage, the application would currently have to wait for the regional data centres to be restored.
Maintenance or patch requires website break in service | M | L | H | The application is deployed across multiple EC2 instances behind a load balancer. | Traffic is automatically targeted to healthy (available) instances meaning that maintenance can be carried out and deployed with minimal application downtime.
Internet Connectivity problems | M | L | L | This is a user issue | This is a user issue
Pandemic affecting word-wide supply chain | L | L | H | Good office hygiene and control visitor access | Enable and set up staff so that all staff can work remotely
Office roster, so that not all staff are simultaneously in the same office every day.
Key person risk assessment | M | H | H | SM8 Application is founded and coded extensively with two key persons holding substantial IP. | Code source in ESCROW. Governed by ESCROW release rules as determined in SLA agreement

## Technological
Technology Risks
1H | 2H | Risk Statement | Management Action
 | ↓ | Rapid advances in technology: | Risk mitigation
|  | It is critical for Sm8rtHealth to continuously ensure its applications and infrastructure are capable to meet clients and market demand. | Award of any IT contract and any related 3rd party vendors is subject to Due Diligence. Keep abreast of likely future IT developments.
Reference supporting documentation
o Security Hardening template
o Vulnerability Management
 | → | Vendor dependency | Risk mitigation
|  | Sm8rtHealth is dependent on two types of vendors, the hosting Service Providers (AWS) and the application development houses we utilize (StyleIT and SaaS) digital as our primary vendor’s. Optimation Group and Solnet Solutions have historically worked on the application and could “take-over” maintenance if required.). | These IT vendors provide primary services for the operations of Sm8rtHealth that are critical to in the service provision for our clients. As a result of Sm8rtHealth’s dependency, a program of risk mitigation is in place.
Reference supporting documentation
o IT Audit Framework
o SM8 - Due Diligence on Outsourcing Vendor
o Separation of Duties between development team and deployment team
o Periodic external audit reviews of vendor capabilities and flows
 | → | Website Failure | Risk mitigation
|  | The goal of 100% perpetual internet connectivity a is desired. High Level Availability (HLA) is influenced predominately by the stability and connectivity of hosted environment AWS which gaurantees a 99% uptime rate | Website failure can be both “planned” and “un-planned”.
Planned: Inevitably our 3rd party IT suppliers and our clients are going to require periods through the year where connectivity is lost or Sm8rtHealth is required to bring the website down. for planned or scheduled maintenance events. These are accommodated for in the Business Continuity Plan
Unplanned: Unplanned website failures can occur due to reasons beyond SM8 control. Mitigating the risk requires immediate response and support escalation procedure. Include:
· Stringent monitors of the website by both SM8 (Monitus) and the Hosting Provider Monitor services.
· Ensure all auto-updates are switched off so that only “plnaned and controlled” updates can occur in the O/S
· Simulate BCP plan
Reference supporting documentation
o BCP and BP procedures
o Incident Response Plans
 | → | Failure in AWS Services or API’s | Risk mitigation:
|  | Use of API’s or web services for white-label and affiliate solutions. | API’s and web-services are essential for the workings of an integrated auto-underwriting solution. Such entry points into the website can be targeted.
|  | AWS as 3rd party vendor providing the hosting solution | Control measures include:
API’s services are IP address restricted and require an authorised access token
Documentation on API and web services require the user to fulfil the requirements of the Access Control Policy.
API’s are subject to penetration testing as a single line item requirements.
API’s must be coded to the heighted possible security level (OWASP standards)
Reference supporting documentation
o SDLCP
o Access control policy
o Penetration Test:- Requirements template
 | ↗ | Security Breach | Risk mitigation:
Each client has their own MSQL instance is to minimize data contamination of security breaches.
|  | SM8 faces the risk of security breaches, computer virus and malicious attacks on the system in some circumstances. Unplanned system downtime (due to failure) could cause major operational disruption and negative customers’ perception. | Security requirements will be identified and agreed prior to the implementation of information systems.
SM8 Strategy to NEVER hold personal data. Where SM8 is responsible for pdf generation then API's will be provided to clients to scrub personal information. Rule of Thumb… max 90 days.
Business continuity plans are also implemented to ensure timely resumptions of the system if there is any dysfunction.
Data in the system can be manually transferred if the system malfunctions.
Reference supporting documentation
o Security Hardening Template
o Access Control Policy
o BCP and BP procedures
o Software Development Life Cycle
o Vulnerability Management
o Patch management Checklist
o Change Management Practise
o Incident Response Plans

## Operational
Operational Risks
1H | 2H | Risk Statement | Management Action
 | → | Customer Support | Risk mitigation:
|  | Sm8rtHealth is responsible for support as per its SLA’s with the various insurers. | Clear documentation of the roles of the respective support partners is essential to prevent Insurer confusion.
Clearly defined achievable SLA’s entered into.
Introduction and education of a South East Asian support vendor for 1st and 2nd level support sought, in order to provide full support during working hours.
 | → | Claim / underwriting risk | Risk mitigation:
6 monthly review and analysis of underwriting rules.
Analysis of issued policies with emphasis on geographical “hot-spots” or specific locations where update is highly skewed.
|  | Claim risks refers to fraudulent claims either through non-disclosure or anti-selection. | Measure disclosure against national statistics where available. Eg Smoker disclosure against National statistics for smoking,
 | → | Fraudulent Sales | Risk Mitigation:
|  | Fraudulent sales can proliferate on the Internet. There is no absolute assurance for the Company to detect or prove fraud at all times. | Develop and implemented vigilant and stringent safeguards and processes by undertaking verification of information furnished by the users. Such as:
· Validating against Insure’s policy admin system for excessive sum assured
· Audit trails through the purchase process
· Underwriting rules that detect possible gaming of the underwriting engine
Regular internal audits will be conducted to assess the adequacy and effectiveness of the internal control to minimise the risk of fraud.
 | → | Non-performing technical support partner/IT vendors | Risk Mitigation:
|  | Substandard services such as continuously delay in service delivery or poor quality of service being provided by the technical support partner /IT vendors. This could adversely affect the revenue generation and lead to operation disruptions | The technical support partners, Solnet Solutions and Optimation Group in Auckland New Zealand and Hitachi Sunway Business Solution and Leo Barnett in SE Asia have significant experience in their particular fields of service.
Agreements have been established to formalise the working relationship with these technical strategic IT vendors.
Reference supporting documentation
o SLA – Solnet Solutions NZ Limited
o SLA- Optimation Group Ltd
o SLA – Hitachi Sunway Snd Bhd
o SLA – Leo Barnett Snd Bhd
Human Resources Risks
1H | 2H | Risk Statement | Management Action
 |  | Dependence on Key | Risk mitigation:
|  | Key individual that can cause disruption to operations | The Directors and project promoters have extensive working experience in the insurance and IT industry. It is their duty to impart this knowledge to key personal.
|  | Silvia Lee - access to guidelines | Access to Accent and Gen Re guidelines can be sourced independently
Succession plan for the key employee will be established. Management also expects the skill level of inexperienced employee will be increase once the on -the job training is provided.

## Business Development
Strategic and Business Development Risks
1H | 2H | Risk Statement | Management Action
 | → | Insufficient market penetration: | Risk Mitigation:
|  | Market penetration or our ability to sell automated underwriting solutions which directly affect the revenue stream and operating cash reserves of the Company | Continue to build the relationship with Hannover-Re and other re-insurer’s to develop leads.
Evolve the proposition so at to minimize the costs to entry for insurers.
Increased efforts for off-shore business in developing markets, with an emphasis on South East Asia, Australia and New Zealand
 | ↗ | Insurer awareness: | Risk Mitigation:
|  | SM8's inability to make insurers aware of its value propositions | Increased expenditure on above-the-line marketing programs such as Insurance conferences and road shows. Emphasis on Actuarial and underwriting and InsureTech conference.
|  | Covid restriction on travel | Look to publish papers and guest speak on SM8 experience in online direct to consumer insurance products.
 | → | Protection products: | Risk Mitigation:
|  | Insurer’s desire for “Guaranteed Issued” products and “underwrite at claim time” lessening the demand for automated underwriting at time of purchase. | Broaden SM8 product range and service offerings. Health and Travel markets to be developed. Work with regulators, and consumers to bring awareness as to the short-comings of simplified issue products.
 | ↓ | Insurer demand: | Risk Mitigation:
|  | Insurer demand for automated underwriting engines | Broaden our offering to integrate into insurance aggregator websites and broker support technologies
Use of SM8 experience and global analytics data to show evidence of:
Better self-disclosure
Managing channel conflict
Cost efficiencies backed by claims experiences
Advancement of “robo-advice”
Less than 5% of insurer’s in our target market offer for Straight Through Processing for either consumer or broker use.
 | → | New entrants: | Risk Mitigation:
|  | InsurTech start-up are abound, with many Insurer’s having incubators in Singapore. Re-insurer are also further enhancing their auto-underwriting solutions to be more agile and sales focused. | Develop an InsureTech strategy to promote SM8 history of innovation in auto-underwriting solutions
Remain Re-insurer-agnostic so to provide SM8 with a competitive edge for insurer’s no looking to be tied into re-insurance arrangements
Remain price competitive and develop pricing models where insurer costs are marginal as opposed to fixed.
 | → | Public Relations: | Risk Mitigation:
|  | Insurer perception of the Sm8rtHealth brand position and propositions is reliant on a good the historical ethos of the underwriting rules. | Heightened testing programs before any launch to public
Maintain and analyze SM8 underwriting rules experience so as to maximize;
Through-put
Minimise claims
Consumer or Broker experience